## Sheet1
Task# | Task | Owner | Status | Completion Date | Dependency | Notes
1.0 | Recommender Training Deck | Max Goff |  | 2017-08-25
1.1 | Brief history of Recommender Systems | Max Goff |  | 2017-08-11
1.1.1 | Content Creation | Max Goff |  | 2017-07-21
1.1.2 | Review | Mo Patel | Max-Mo to review | 2017-08-04
1.1.3 | Post-Review Changes and Finalize | Max Goff |  | 2017-08-11
1.2 | Colaborative filtering (high level to in-depth math) | Max Goff |  | 2017-08-11
1.3 | Cold start challenges | Max Goff |  | 2017-08-11
1.4 | Sparse data issues | Max Goff |  | 2017-08-11
1.5 | Wide overview and in-depth | Max Goff |  | 2017-08-11
1.6 | Deep overview and in-depth | Max Goff |  | 2017-08-11
1.7 | Review and Refactor | Mo Patel |  | 2017-08-14
1.8 | Deep Learning foundation | Max Goff |  | 2017-08-14
1.9 | Review and Refactor | Mo Patel |  | 2017-08-17
2.0 | Recommender Training Lab | Mo Patel | Will stand up when GPUs are needed | 2017-08-14
2.1 | Data Description Notebook | Cynthia Li |  | 2017-08-11
| Data Source Background | Cynthia Li |  | 2017-08-11
| Data Loading | Cynthia Li |  | 2017-08-11
| Data Exploration | Cynthia Li |  | 2017-08-11
2.2 | Collaborative Filtering Notebook | Cynthia Li |  | 2017-08-11
2.2.1 | Build Collaborative Filtering Model | Cynthia Li |  | 2017-08-11
2.2.2 | Test/Evaluate Collaborative Filtering Model | Cynthia Li |  | 2017-08-11
2.2.3 | Deploy Collaborative Filtering Model | Cynthia Li |  | 2017-08-11
2.2.4 | Review Notebooks | Mo Patel |  | 2017-08-15
2.3 | Wide & Deep Notebook | Westa Domoneva |  | 2017-08-14
2.3.1 | Build Deep & Wide Model | Westa Domoneva |  | 2017-08-14
2.3.2 | Test/Evaluate Deep & Wide Model | Westa Domoneva |  | 2017-08-14
2.3.3 | Deploy Deep & Wide Model | Westa Domoneva |  | 2017-08-14
2.3.4 | Review Notebooks | Mo Patel |  | 2017-08-15
3.0 | Review and Feedback | Mo Patel and Others |  | 2017-08-21