## Sheet1
Task# | Task | Owner | Status | Completion Date | Dependency | Notes
1.0 | Recommender Training Deck | Max Goff |  | 2017-08-25
1.1 | Brief history of Recommender Systems | Max Goff |  | 2017-08-11
1.1.1 | Content Creation | Max Goff |  | 2017-07-21
1.1.2 | Review | Mo Patel | Max-Mo to review | 2017-08-04
1.1.3 | Post-Review Changes and Finalize | Max Goff |  | 8/111
1.2 | Colaborative filtering (high level to in-depth math)
1.3 | Cold start challenges
1.4 | Sparse data issues
1.5 | Wide overview and in-depth
1.6 | Deep overview and in-depth
2.0 | Recommender Training Lab
2.1 | Data Description Notebook
Data Source Background
Data Loading
Data Exploration
2.2 | Collaborative Filtering Notebook
2.2.1 | Build Collaborative Filtering Model |  |  |  |  | https://www.codementor.io/jadianes/building-a-recommender-with-apache-spark-python-example-app-part1-du1083qbw
2.2.2 | Test/Evaluate Collaborative Filtering Model
2.2.3 | Deploy Collaborative Filtering Model
2.3 | Wide & Deep Notebook